## General Study Plan
[45 empty] | Student ID |  |  | 59210500
| Name | Chutina Jansakul |  |  | Student ID |  |  | 59210500 |  |  |  |  | Academic timeline for | [5 empty] | Ph.D.
| Program in |  | Biomedical Science |  |  |  |  | School of |  |  | Public Health
Activity |  |  |  | Month
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
|  |  |  | Mar, 2019 | Apr, 2019 | May, 2019 | Jun, 2019 | Jul, 2019 | Aug, 2019 | Sep, 2019 | Oct, 2019 | Nov, 2019 | Dec, 2019 | Jan, 2020 | Feb, 2020 | Mar, 2020 | Apr, 2020 | May, 2020 | Jun, 2020 | Jul, 2020 | Aug, 2020 | Sep, 2020 | Oct, 2020 | Nov, 2020 | Dec, 2020 | Jan, 2021 | Feb, 2021 | Mar, 2021 | Apr, 2021 | May, 2021 | Jun, 2021 | Jul, 2021 | Aug, 2021 | Sep, 2021 | Oct, 2021 | Nov, 2021 | Dec, 2021 | Jan, 2022 | Feb, 2022 | Mar, 2022 | Apr, 2022 | May, 2022 | Jun, 2022 | Jul, 2022 | Aug, 2022 | Sep, 2022 | Oct, 2022 | Nov, 2022 | Dec, 2022 | Jan, 2023 | Feb, 2023
1 | Qualifying Examination
2 | Carry out preliminary study, write thesis proposal and submit full proposal to thesis proposal committee | bar: Month 1 to Month 3
3 | Proposal Examination | bar: Month 3
4 | Perform Research Work | bar: Month 4 to Month 21
5 | Write a research article for publication | bar: Month 20 to Month 24
6 | Write up a thesis | bar: Month 23 to Month 25
7 | Submit the thesis to advisor for suggestion | bar: Month 25 to Month 27
8 | Submit the thesis checked and approved by advisor to the thesis committee | bar: Month 26 to Month 28
9 | Thesis defense (with achievement of 'S') | bar: Month 28
10 | Thesis revision | bar: Month 28 to Month 29
11 | Thesis submission to College of Graduate Studies (Format check) | bar: Month 28 to Month 29
12 | Complete Thesis Submission to School, CLM, CGS | bar: Month 29

## Research Study Plan
แผนการดำเนินงานวิจัย (Research Gantt Chart)
|  |  |  | ทุนอุดหนุนโครงการวิจัยสำหรับนักศึกษาระดับบัณฑิตศึกษา ประจำปีงบประมาณ พ.ศ. | 2563
| ชื่อ-นามสกุล | รหัสนักศึกษา
| หลักสูตร |  | สำนักวิชา
กิจกรรม เดือน/ปี
1
2
3
4
5
6
7
8
9
10
11
12
13
14